# NextOps Project Status Brief

Completed Work and Remaining Delivery Plan

Status date  21 September 2026

The four Ubuntu servers and their role package layers are prepared, and the local CPU model has passed a bounded authenticated smoke test. The next phase is controlled service deployment, read-only Zabbix integration, recovery proof, and full offline acceptance.

Prepared for project presentation

# Executive Summary

NextOps has moved beyond architecture-only planning. The repository contains tested application and inference foundations, all four role servers have passed a sanitized qualification, the required native packages are installed, and the pinned local model has generated fresh Persian and English responses on the AI server. The project is not yet a production deployment: the production databases and Zabbix are not initialized, the application and connector are not deployed, and Internet-blocked end-to-end acceptance has not run.

# Status at a Glance

| Workstream | Status | Verified result | Remaining acceptance |
| --- | --- | --- | --- |
| Architecture | Accepted baseline | Phase 0 and ADRs 0001–0006 accepted | Continue operation-specific approvals |
| Application | Source implemented | Identity, policy, PostgreSQL, durable work, audit, API | Package and deploy; add TLS, UI, backup and restore |
| Four servers | Qualified and prepared | Ubuntu 24.04.5, healthy systemd, UFW, SSH-only wildcard listener | Install configuration and perform service acceptance |
| CPU inference | Smoke-tested | Pinned runtime and model verified; bilingual loopback generation | Production unit plus quality, load, failure and offline tests |
| Zabbix and connector | Package layer only | Zabbix stack installed but inactive; connector environment prepared | Initialize Zabbix and deploy the restricted reader |
| Offline milestone | Not demonstrated | Contracts and acceptance cases are defined | Prove fresh evidence-linked answers with WAN blocked |

# Work Completed

## Architecture Requirements and Safety

The owner accepted Phase 0, the Stage 1A–1E delivery path, and ADRs 0001–0006.

The initial four virtual machines total 40 vCPU, 184 GiB RAM, and 980 GiB virtual disk.

All AI generation remains local and CPU-only. There is no GPU dependency or cloud inference fallback.

Phase 1 remains read-only. The model receives neither target credentials nor authority to approve changes.

## Repository and Application Foundation

Stage 1A implements Argon2id identity bootstrap, login and recovery; opaque hashed sessions; PostgreSQL and Alembic migrations; idempotent durable runs; expiring worker leases; append-restricted audit; and an authenticated FastAPI surface.

Stage 1B implements a runtime-neutral LLMProvider, authenticated inference boundaries, a loopback llama.cpp adapter, one-active/two-queued scheduling, bounded inputs and outputs, cancellation, safe readiness, and explicit overload and dependency failures.

Four schema-validated deployment dossiers and guarded installers define the public role handoff without committing private infrastructure identifiers or credentials.

## Server Qualification and Package Preparation

All four clean Ubuntu 24.04.5 LTS guests passed host-key, key-only authentication, direct-root denial, resource, mount, time, VMware Tools, firewall, listener, update, reboot, and system-health checks.

Role packages were installed through the existing strict proxy chain without a broad operating-system upgrade. Automatic service starts and automatic PostgreSQL cluster creation were blocked.

The app host has PostgreSQL 16.15 and Nginx 1.24. AI has GCC 13.3, CMake 3.28, Ninja 1.11, OpenBLAS 0.3.26, and uv 0.12.17. Connectors has Python 3.12 virtual-environment support. Zabbix has Zabbix 7.0.30, PostgreSQL 16.15, Nginx 1.24, PHP 8.3.6, the frontend, SQL scripts, and Agent 2.

Protected non-login service identities and role directories exist. Product, database, and web services remain inactive and disabled by design.

Docker was not installed because the selected native systemd design does not require it and a container socket would expand the trust boundary.

## Local CPU Model Evidence

The pinned llama.cpp revision was built in Release mode with native CPU settings, OpenMP, and OpenBLAS, with no GPU linkage. Its promoted binary checksum is recorded in the inference manifest.

The pinned Qwen3-8B-Q4_K_M model is 5,027,783,488 bytes and matched its expected SHA-256 before and after promotion to the protected model volume.

A temporary authenticated loopback service used one slot, an 8K context, zero GPU layers, and no Web UI. It cold-started in 7 seconds, returned READY in 630 ms and آماده in 1,431 ms, then stopped without a residual process or listener.

This is bounded smoke evidence, not production, quality, sustained-load, recovery, or Internet-blocked acceptance.

## Verification Completed

Repository formatting, lint, strict typing, documentation, deployment-dossier, inference-artifact, and installer validation passed for the reviewed revision.

The desktop suite passed 71 non-integration tests; five database tests were skipped because no local PostgreSQL URL was supplied.

On the application server, the same revision passed formatting, lint, strict typing, all 71 non-integration tests, and all five PostgreSQL integration tests against an isolated PostgreSQL 16.15 cluster that was removed afterward.

# Work Remaining

## Stage 1B Production Inference Service

Install the reviewed nextops-ai systemd unit and root-owned configuration, keep the listener on loopback, reference secrets safely, apply CPU and memory limits, and test authentication, health, restart, logging, overload, cancellation, timeout, rollback, bilingual quality, load, and Internet-blocked cold start.

## Stage 1A Application Deployment

Package the offline release, initialize PostgreSQL 16 on the dedicated mount, create least-privilege roles, run migrations, bootstrap identity, deploy API and worker services, configure Nginx and TLS, and complete the browser UI, secret delivery, backup, restore, and rollback tests.

## Zabbix Prerequisite

Initialize the Zabbix database, import its schema, configure Zabbix Server, Nginx, PHP-FPM, and Agent 2, establish local administrator recovery, enable self-monitoring, verify retention against actual growth, and create a restricted read-only API identity.

## Read-only Connector and First Useful Answer

Deploy the gateway and isolated Zabbix runner. Give only that runner the scoped token, allow only listed read methods, bound result size and time, compute counts in code, and demonstrate a fresh Persian and English question with current Zabbix evidence, local CPU explanation, source time, scope, and audit.

## Offline and Recovery Acceptance

With WAN access blocked, prove cold starts, fresh local login, revoked-token and unreachable-target handling, stale-data labeling, low-space behavior, resource limits, independent backups, restore drills, and release rollback across all four servers and a fresh client.

# Recommended Delivery Sequence

1. Productionize the AI service and complete the Stage 1B bilingual offline evaluation.

2. Package and deploy the application database, API, worker, reverse proxy, TLS, secrets, backup, and restore path.

3. Initialize Zabbix and establish the restricted read-only API identity.

4. Deploy the connector and complete live bounded Stage 1C reads.

5. Demonstrate the Stage 1D evidence-linked answer and complete Stage 1E offline and recovery acceptance.

# Presentation Conclusion

The infrastructure and software foundations are ready for controlled service deployment. NextOps now has verified hosts, installed role packages, tested repository foundations, and a working local CPU model artifact. The remaining work is production configuration, stateful-service initialization, read-only integration, recovery proof, and full offline acceptance. Until those gates pass, the accurate status is prepared and partially validated, not production-ready.

# گزارش وضعیت اجرایی پروژه NextOps

کارهای انجام‌شده و برنامهٔ ادامهٔ تحویل

تاریخ وضعیت  ۳۰ شهریور ۱۴۰۵  برابر با ۲۱ سپتامبر ۲۰۲۶

هر چهار سرور Ubuntu و بسته‌های هر نقش آماده شده‌اند و مدل محلی روی CPU یک smoke test محدود و احرازهویت‌شده را با موفقیت گذرانده است. گام بعدی، استقرار کنترل‌شدهٔ سرویس‌ها، اتصال فقط‌خواندنی Zabbix، اثبات بازیابی و پذیرش کامل آفلاین است.

تهیه‌شده برای ارائهٔ وضعیت پروژه

# جمع‌بندی مدیریتی

NextOps از مرحلهٔ صرفاً معماری عبور کرده است. مخزن اکنون پایهٔ آزمودهٔ برنامه و سرویس inference را دارد؛ چهار سرور نقش‌محور بررسی شده‌اند؛ بسته‌های لازم نصب شده‌اند؛ و مدل محلی روی سرور AI پاسخ تازهٔ فارسی و انگلیسی تولید کرده است. با این حال، سامانه هنوز استقرار تولیدی نیست: پایگاه‌های تولید و Zabbix مقداردهی نشده‌اند، برنامه و connector مستقر نیستند و پذیرش سرتاسری با اینترنت قطع انجام نشده است.

# نمای کلی وضعیت

| پذیرش باقی‌مانده | نتیجهٔ تأییدشده | وضعیت | محور کار |
| --- | --- | --- | --- |
| ادامهٔ مجوز جداگانه برای هر عملیات | مرحلهٔ صفر و ADRهای 0001 تا 0006 پذیرفته شده‌اند | مبنای پذیرفته‌شده | معماری |
| بسته‌بندی و استقرار، TLS، UI، backup و restore | هویت، policy، PostgreSQL، کار ماندگار، audit و API | پیاده‌سازی در source | برنامه |
| نصب پیکربندی و پذیرش سرویس | Ubuntu 24.04.5، systemd سالم، UFW و فقط SSH عمومی | صلاحیت‌سنجی و آماده | چهار سرور |
| unit تولید و آزمون کیفیت، بار، خطا و آفلاین | runtime و مدل ثابت؛ تولید دوزبانه روی loopback | smoke test موفق | inference روی CPU |
| مقداردهی Zabbix و استقرار reader محدود | stack نصب اما غیرفعال و محیط connector آماده | فقط لایهٔ package | Zabbix و connector |
| اثبات پاسخ تازه و مستند با WAN قطع | قرارداد و موارد پذیرش تعریف شده‌اند | هنوز اثبات نشده | خروجی آفلاین |

# کارهای انجام‌شده

## معماری نیازمندی‌ها و ایمنی

مالک، مرحلهٔ صفر، مسیر تحویل 1A تا 1E و ADRهای 0001 تا 0006 را پذیرفته است.

چهار ماشین اولیه در مجموع ۴۰ vCPU، حافظهٔ ۱۸۴ GiB و دیسک مجازی ۹۸۰ GiB دارند.

تولید پاسخ فقط روی CPU محلی است و هیچ وابستگی به GPU یا fallback ابری وجود ندارد.

مرحلهٔ یک فقط‌خواندنی است و مدل نه credential مقصد دارد و نه اختیار تأیید تغییر.

## پایهٔ مخزن و برنامه

مرحلهٔ 1A شامل هویت Argon2id، session غیرشفاف و hash‌شده، PostgreSQL و Alembic، run ماندگار و idempotent، lease منقضی‌شونده، audit محدود به append و FastAPI احرازهویت‌شده است.

مرحلهٔ 1B قرارداد LLMProvider، مرزهای احرازهویت‌شدهٔ inference، adapter فقط-loopback، صف یک درخواست فعال و دو درخواست منتظر، حدود ورودی و خروجی، cancellation، readiness امن و خطاهای صریح را دارد.

چهار پروندهٔ معتبرشده با schema و installerهای محافظت‌شده، تحویل هر نقش را بدون انتشار شناسه یا credential خصوصی تعریف می‌کنند.

## صلاحیت‌سنجی سرورها و آماده‌سازی بسته‌ها

هر چهار مهمان Ubuntu 24.04.5 LTS کنترل کلید میزبان، احراز هویت فقط با کلید، رد root مستقیم، منابع، mount، زمان، VMware Tools، firewall، listener، update، reboot و سلامت سیستم را گذرانده‌اند.

بسته‌های هر نقش از proxy سخت‌گیرانهٔ موجود و بدون ارتقای کلی سیستم‌عامل نصب شدند. شروع خودکار سرویس و ایجاد خودکار cluster در PostgreSQL مسدود شد.

میزبان برنامه PostgreSQL 16.15 و Nginx 1.24 دارد. AI دارای GCC 13.3، CMake 3.28، Ninja 1.11، OpenBLAS 0.3.26 و uv 0.12.17 است. connector از محیط مجازی Python 3.12 پشتیبانی می‌کند. میزبان پایش Zabbix 7.0.30، PostgreSQL 16.15، Nginx 1.24، PHP 8.3.6، frontend، scriptهای SQL و Agent 2 را دارد.

هویت‌های بدون login و مسیرهای محافظت‌شده ساخته شده‌اند و سرویس‌های محصول، پایگاه و وب طبق برنامه inactive و disabled مانده‌اند.

Docker نصب نشد، زیرا طراحی native systemd به آن نیاز ندارد و container socket مرز اعتماد را گسترش می‌دهد.

## شاهد مدل محلی روی CPU

revision ثابت llama.cpp در حالت Release با تنظیم native CPU، OpenMP و OpenBLAS و بدون پیوند GPU ساخته شد و checksum آن در manifest ثبت است.

فایل Qwen3-8B-Q4_K_M برابر ۵٬۰۲۷٬۷۸۳٬۴۸۸ بایت است و SHA-256 آن پیش و پس از انتقال به حجم محافظت‌شده برابر بود.

سرویس موقت و احرازهویت‌شده فقط روی loopback، با یک slot، context برابر 8K، لایهٔ GPU صفر و Web UI غیرفعال اجرا شد. شروع سرد ۷ ثانیه بود؛ READY در ۶۳۰ میلی‌ثانیه و آماده در ۱۴۳۱ میلی‌ثانیه برگردانده شد و process یا listener باقی نماند.

این نتیجه فقط smoke test محدود است و پذیرش تولید، کیفیت، بار پایدار، بازیابی یا کارکرد با اینترنت قطع‌شده محسوب نمی‌شود.

## اعتبارسنجی انجام‌شده

format، lint، type سخت‌گیرانه، مستندات، پرونده‌های استقرار، artifactهای inference و installerها برای revision بازبینی‌شده قبول شدند.

روی desktop، هر ۷۱ آزمون non-integration قبول و پنج آزمون پایگاه به‌دلیل نبود URL محلی PostgreSQL به‌درستی skip شدند.

روی سرور برنامه، همان revision از format، lint و type عبور کرد؛ هر ۷۱ آزمون non-integration و هر پنج آزمون integration روی cluster جداشدهٔ PostgreSQL 16.15 قبول شدند و cluster سپس حذف شد.

# کارهای باقی‌مانده

## سرویس تولید inference در مرحلهٔ 1B

unit بازبینی‌شدهٔ nextops-ai و پیکربندی متعلق به root نصب شود؛ اتصال فقط روی loopback بماند؛ secretها امن ارجاع داده شوند؛ حدود CPU و حافظه اعمال شود؛ و احراز هویت، health، restart، log، overload، cancellation، timeout، rollback، کیفیت دوزبانه، بار و شروع سرد با اینترنت قطع آزموده شوند.

## استقرار برنامه در مرحلهٔ 1A

release آفلاین بسته‌بندی، PostgreSQL 16 روی mount اختصاصی مقداردهی، roleهای کم‌دسترسی ساخته، migration اجرا، هویت bootstrap و سرویس‌های API و worker مستقر شوند. Nginx و TLS، UI مرورگر، تحویل secret، backup، restore و rollback نیز تکمیل شوند.

## پیش‌نیاز Zabbix

پایگاه Zabbix مقداردهی و schema وارد شود؛ Zabbix Server، Nginx، PHP-FPM و Agent 2 پیکربندی شوند؛ بازیابی مدیر محلی، self-monitoring، سنجش retention با رشد واقعی و هویت API فقط‌خواندنی و محدود برقرار شوند.

## connector فقط‌خواندنی و نخستین پاسخ کاربردی

gateway و runner جداشدهٔ Zabbix مستقر شوند. توکن محدود فقط در اختیار runner باشد، تنها روش‌های read فهرست‌شده مجاز باشند و اندازه و زمان پاسخ محدود شود. سپس سؤال تازهٔ فارسی و انگلیسی با شاهد جاری Zabbix، توضیح محلی CPU، زمان منبع، دامنه و audit نمایش داده شود.

## پذیرش آفلاین و بازیابی

با WAN قطع، شروع سرد همهٔ سرویس‌ها، ورود تازهٔ محلی، رفتار در برابر توکن باطل و مقصد خارج از دسترس، برچسب دادهٔ قدیمی، کمبود فضا، سقف منابع، backup مستقل، restore و rollback روی هر چهار سرور و client تازه اثبات شوند.

# ترتیب پیشنهادی ادامهٔ کار

۱. سرویس AI تولیدی و ارزیابی دوزبانه و آفلاین مرحلهٔ 1B تکمیل شود.

۲. پایگاه، API، worker، reverse proxy، TLS، secret، backup و restore برنامه بسته‌بندی و مستقر شوند.

۳. Zabbix مقداردهی و هویت API فقط‌خواندنی و محدود ایجاد شود.

۴. connector مستقر و خواندن زنده و محدود مرحلهٔ 1C کامل شود.

۵. پاسخ مستند مرحلهٔ 1D نمایش داده شود و پذیرش آفلاین و بازیابی مرحلهٔ 1E پایان یابد.

# نتیجهٔ قابل ارائه

زیرساخت و پایهٔ نرم‌افزار برای آغاز استقرار کنترل‌شدهٔ سرویس‌ها آماده است. NextOps اکنون سرورهای تأییدشده، بسته‌های نصب‌شدهٔ هر نقش، پایهٔ مخزن آزموده و artifact عملیاتی مدل محلی روی CPU دارد. کار باقی‌مانده شامل پیکربندی تولید، مقداردهی سرویس‌های stateful، اتصال فقط‌خواندنی، اثبات بازیابی و پذیرش کامل آفلاین است. تا عبور از این دروازه‌ها، وضعیت دقیق پروژه آماده‌شده و تا حدی اعتبارسنجی‌شده است، نه آمادهٔ بهره‌برداری تولیدی.